## Calendar external
Week number | Start Date | End Date | Activity type | Activities | Comments
45 | 2026-11-02 | 2026-11-05 | Schedule | T2 Synchronised Standard day
45 | 2026-11-02 | 2026-11-06 | Release testing | R2026.NOV Release testing
45 | 2026-11-04 | 2026-11-04 | Special testing | BILL invoice for NCBs | Billing period 19-31 October
45 | 2026-11-04 | 2026-11-04 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
45 | 2026-11-04 | 2026-11-04 | Special testing | Open ECONSII from 10:00 - 12:00 CET
45 | 2026-11-05 | 2026-11-05 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
45 | 2026-11-06 | 2026-11-06 | Release deployment | T2 R2026.NOV deployment (Package 12) | critical RD only
45 | 2026-11-06 | 2026-11-06 | Schedule | T2 Synchronised Release day
46 | 2026-11-09 | 2026-11-11 | Release testing | R2026.NOV Release testing
46 | 2026-11-09 | 2026-11-12 | Schedule | T2 Synchronised Standard day
46 | 2026-11-11 | 2026-11-11 | Special testing | Open ECONSII from 10:00 - 12:00 CET
46 | 2026-11-11 | 2026-11-11 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
46 | 2026-11-12 | 2026-11-12 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
46 | 2026-11-13 | 2026-11-13 | Release deployment | T2 R2026.NOV deployment (Package 13) | critical RD only
46 | 2026-11-13 | 2026-11-13 | Schedule | T2 Synchronised Release day
47 | 2026-11-16 | 2026-11-19 | Schedule | T2 Synchronised Standard day
47 | 2026-11-18 | 2026-11-18 | Special testing | BILL invoice for NCBs | Billing period 1-15 November
47 | 2026-11-18 | 2026-11-18 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
47 | 2026-11-18 | 2026-11-18 | Special testing | Open ECONSII from 10:00 - 12:00 CET
47 | 2026-11-19 | 2026-11-19 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
47 | 2026-11-20 | 2026-11-20 | Release deployment | T2 R2026.NOV deployment (Package 14) | critical RD only
47 | 2026-11-20 | 2026-11-20 | Schedule | T2 Synchronised Release day
48 | 2026-11-23 | 2026-11-26 | Schedule | T2 Synchronised Standard day
48 | 2026-11-25 | 2026-11-25 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
48 | 2026-11-25 | 2026-11-25 | Special testing | Open ECONSII from 09:00 - 14:00 CET | as per request from FRCB and DECB with possible risk to not have ECMS contingency mode
48 | 2026-11-26 | 2026-11-26 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
48 | 2026-11-27 | 2026-11-27 | Schedule | T2 Synchronised Release day
49 | 2026-11-30 | 2026-12-03 | Schedule | T2 Synchronised Standard day
49 | 2026-12-02 | 2026-12-02 | ORT | T2S ORT: RAD Tests (Inter regional failover with loss of data) | Impact on T2 UTEST: T2 EoD and SoD events will be rescheduled to an earlier point in time
49 | 2026-12-02 | 2026-12-02 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
49 | 2026-12-02 | 2026-12-02 | Special testing | Open ECONSII from 10:00 - 12:00 CET
49 | 2026-12-03 | 2026-12-03 | Special testing | BILL invoice for NCBs | Billing period 16-30 November
49 | 2026-12-03 | 2026-12-03 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
49 | 2026-12-04 | 2026-12-04 | Schedule | T2 Synchronised Release day
50 | 2026-12-07 | 2026-12-10 | Schedule | T2 Synchronised Standard day
50 | 2026-12-09 | 2026-12-09 | Special testing | Open ECONSII from 10:00 - 12:00 CET
50 | 2026-12-09 | 2026-12-09 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
50 | 2026-12-10 | 2026-12-10 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
50 | 2026-12-11 | 2026-12-11 | Schedule | T2 Synchronised Release day
51 | 2026-12-14 | 2026-12-17 | Schedule | T2 Synchronised Standard day
51 | 2026-12-15 | 2026-12-15 | Special testing | Open ECONSII from 10:00 - 12:00 CET | As per request from NLCB - no ECMS contingency mode activation needed.
51 | 2026-12-16 | 2026-12-16 | Special testing | BILL invoice for NCBs | Billing period 1-13 December
51 | 2026-12-16 | 2026-12-16 | Special testing | Open ECONSII from 10:00 - 12:00 CET
51 | 2026-12-16 | 2026-12-16 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
51 | 2026-12-17 | 2026-12-17 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
51 | 2026-12-18 | 2026-12-18 | Schedule | T2 Synchronised Release day
52 | 2026-12-21 | 2026-12-23 | Schedule | T2 Synchronised Standard day
52 | 2026-12-23 | 2026-12-23 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
52 | 2026-12-23 | 2026-12-23 | Special testing | Open ECONSII from 10:00 - 12:00 CET
52 | 2026-12-24 | 2026-12-24 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
52 | 2026-12-24 | 2026-12-24 | Schedule | T2 closing day
52 | 2026-12-25 | 2026-12-25 | Schedule | T2 closing day
1 | 2026-12-28 | 2026-12-30 | Schedule | T2 Synchronised Standard day
1 | 2026-12-30 | 2026-12-30 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
1 | 2026-12-31 | 2026-12-31 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
1 | 2026-12-31 | 2026-12-31 | Schedule | T2 closing day
1 | 2027-01-01 | 2027-01-01 | Schedule | T2 closing day
2 | 2027-01-04 | 2027-01-07 | Schedule | T2 Synchronised Standard Day
2 | 2027-01-06 | 2027-01-06 | Special testing | BILL invoice for NCBs | Billing period 14-31 December
2 | 2027-01-06 | 2027-01-06 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
2 | 2027-01-07 | 2027-01-07 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
2 | 2027-01-08 | 2027-01-08 | Schedule | T2 Synchronised Release Day
3 | 2027-01-11 | 2027-01-14 | Schedule | T2 Synchronised Standard Day
3 | 2027-01-13 | 2027-01-13 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
3 | 2027-01-14 | 2027-01-14 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
3 | 2027-01-15 | 2027-01-15 | Schedule | T2 Synchronised Release Day
4 | 2027-01-18 | 2027-01-21 | Schedule | T2 Synchronised Standard Day
4 | 2027-01-20 | 2027-01-20 | Special testing | [PLACEHOLDER] BILL invoice for NCBs | Billing period 01-17 January
4 | 2027-01-20 | 2027-01-20 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
4 | 2027-01-21 | 2027-01-21 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
4 | 2027-01-22 | 2027-01-22 | Schedule | T2 Synchronised Release Day
5 | 2027-01-25 | 2027-01-28 | Schedule | T2 Synchronised Standard Day
5 | 2027-01-27 | 2027-01-27 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
5 | 2027-01-28 | 2027-01-28 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
5 | 2027-01-29 | 2027-01-29 | Schedule | T2 Synchronised Release Day
6 | 2027-02-01 | 2027-02-04 | Schedule | T2 Synchronised Standard Day
6 | 2027-02-03 | 2027-02-03 | Special testing | [PLACEHOLDER] BILL invoice for NCBs | Billing period 17-31 January
6 | 2027-02-03 | 2027-02-03 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
6 | 2027-02-04 | 2027-02-04 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
6 | 2027-02-05 | 2027-02-05 | Schedule | T2 Synchronised Release Day
7 | 2027-02-08 | 2027-02-11 | Schedule | T2 Synchronised Standard Day
7 | 2027-02-10 | 2027-02-10 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
7 | 2027-02-11 | 2027-02-11 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
7 | 2027-02-12 | 2027-02-12 | Schedule | T2 Synchronised Release Day
8 | 2027-02-15 | 2027-02-18 | Schedule | T2 Synchronised Standard Day
8 | 2027-02-17 | 2027-02-17 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
8 | 2027-02-18 | 2027-02-18 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
8 | 2027-02-19 | 2027-02-19 | Schedule | T2 Synchronised Release Day
9 | 2027-02-22 | 2027-02-25 | Schedule | T2 Synchronised Standard Day
9 | 2027-02-24 | 2027-02-24 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
9 | 2027-02-25 | 2027-02-25 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
9 | 2027-02-26 | 2027-02-26 | Schedule | T2 Synchronised Release Day
10 | 2027-03-01 | 2027-03-04 | Schedule | T2 Synchronised Standard Day
10 | 2027-03-03 | 2027-03-03 | Special testing | BILL invoice for NCBs | Billing period for full February, as approved accross governances and upon request from a CB.
10 | 2027-03-03 | 2027-03-03 | Special testing | [PLACEHOLDER] BILL invoice for NCBs | Billing period 01-28 February. Full month agreed through OMG WP.
10 | 2027-03-03 | 2027-03-03 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
10 | 2027-03-04 | 2027-03-04 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
10 | 2027-03-05 | 2027-03-05 | Schedule | T2 Synchronised Release Day
11 | 2027-03-08 | 2027-03-11 | Schedule | T2 Synchronised Standard Day
11 | 2027-03-10 | 2027-03-10 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
11 | 2027-03-11 | 2027-03-11 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
11 | 2027-03-12 | 2027-03-12 | Schedule | T2 Synchronised Release Day
12 | 2027-03-15 | 2027-03-18 | Schedule | T2 Synchronised Standard Day
12 | 2027-03-17 | 2027-03-17 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
12 | 2027-03-18 | 2027-03-18 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
12 | 2027-03-19 | 2027-03-19 | Schedule | T2 Synchronised Release Day
13 | 2027-03-22 | 2027-03-24 | Schedule | T2 Synchronised Standard Day
13 | 2027-03-24 | 2027-03-24 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
13 | 2027-03-25 | 2027-03-25 | Schedule | T2 closing day for DKK settlement; T2 Synchronised Standard Day for EUR Settlement | Maundy Thursday for DKK
13 | 2027-03-25 | 2027-03-25 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
13 | 2027-03-26 | 2027-03-26 | Schedule | T2 Closing Day | Good Friday
14 | 2027-03-29 | 2027-03-29 | Schedule | T2 Closing Day | Easter Monday
14 | 2027-03-30 | 2027-03-31 | Schedule | T2 Synchronised Standard Day
14 | 2027-03-31 | 2027-03-31 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
14 | 2027-04-01 | 2027-04-01 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
14 | 2027-04-01 | 2027-04-01 | Schedule | T2 Synchronised Release Day | Due to deployment activities
14 | 2027-04-02 | 2027-04-02 | Schedule | T2 Closing Day | due to First Packages deployment to UTEST
14 | 2027-04-02 | 2027-04-02 | Release deployment | T2 R2027.JUN deployment to Pre-production
15 | 2027-04-05 | 2027-04-08 | Schedule | T2 Synchronised Standard Day
15 | 2027-04-07 | 2027-04-07 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
15 | 2027-04-08 | 2027-04-08 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
15 | 2027-04-09 | 2027-04-09 | Schedule | T2 Synchronised Release Day
16 | 2027-04-12 | 2027-04-15 | Schedule | T2 Synchronised Standard Day
16 | 2027-04-14 | 2027-04-14 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
16 | 2027-04-15 | 2027-04-15 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
16 | 2027-04-16 | 2027-04-16 | Release deployment | T2 R2027.JUN deployment (Package 6) | RD only
16 | 2027-04-16 | 2027-04-16 | Schedule | T2 Synchronised Release Day
17 | 2027-04-19 | 2027-04-22 | Schedule | T2 Live Timing Day | Approved accross WGs upon OMG request : "T+1".
17 | 2027-04-21 | 2027-04-21 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
17 | 2027-04-22 | 2027-04-22 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
17 | 2027-04-23 | 2027-04-23 | Release deployment | T2 R2027.JUN deployment (Package 7) | Critical RD only
17 | 2027-04-23 | 2027-04-23 | Schedule | T2 Live Timing Day | Approved accross WGs upon OMG request : "T+1".
18 | 2027-04-26 | 2027-04-29 | Schedule | T2 Live Timing Day | Approved accross WGs upon OMG request : "T+1".
18 | 2027-04-28 | 2027-04-28 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
18 | 2027-04-29 | 2027-04-29 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
18 | 2027-04-30 | 2027-04-30 | Release deployment | T2 R2027.JUN deployment (Package 8) | Critical RD only
18 | 2027-04-30 | 2027-04-30 | Schedule | T2 Live Timing Day | Approved accross WGs upon OMG request : "T+1".
19 | 2027-05-03 | 2027-05-05 | Schedule | T2 Synchronised Standard Day
19 | 2027-05-05 | 2027-05-05 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
19 | 2027-05-06 | 2027-05-06 | Schedule | T2 closing day for DKK settlement; Synchronised Standard day for EUR settlement | DKK public holiday : Ascension Day
19 | 2027-05-06 | 2027-05-06 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
19 | 2027-05-07 | 2027-05-07 | Release deployment | T2 R2027.JUN deployment (Package 9) | Critical RD only
19 | 2027-05-07 | 2027-05-07 | Schedule | T2 closing day for DKK settlement; Synchronised Release day for EUR settlement | DKK public holiday
20 | 2027-05-10 | 2027-05-13 | Schedule | T2 Synchronised Standard Day
20 | 2027-05-12 | 2027-05-12 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
20 | 2027-05-13 | 2027-05-13 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
20 | 2027-05-14 | 2027-05-14 | Release deployment | T2 R2027.JUN deployment (Package 10) | Critical RD only
20 | 2027-05-14 | 2027-05-14 | Schedule | T2 Synchronised Release Day
21 | 2027-05-17 | 2027-05-17 | Schedule | T2 closing day for DKK settlement; Live Timing day for EUR settlement | DKK public holiday: Whit Monday
21 | 2027-05-18 | 2027-05-20 | Schedule | T2 Live Timing Day | Approved accross WGs upon OMG request : "T+1".
21 | 2027-05-19 | 2027-05-19 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
21 | 2027-05-20 | 2027-05-20 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
21 | 2027-05-21 | 2027-05-21 | Release deployment | T2 R2027.JUN deployment (Package 11) | Critical RD only
21 | 2027-05-21 | 2027-05-21 | Schedule | T2 Live Timing Day | Approved accross WGs upon OMG request : "T+1".
22 | 2027-05-24 | 2027-05-27 | Schedule | T2 Live Timing Day | Approved accross WGs upon OMG request : "T+1".
22 | 2027-05-26 | 2027-05-26 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
22 | 2027-05-27 | 2027-05-27 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
22 | 2027-05-28 | 2027-05-28 | Release deployment | T2 R2027.JUN deployment (Package 12) | Critical RD only
22 | 2027-05-28 | 2027-05-28 | Schedule | T2 Live Timing Day | Approved accross WGs upon OMG request : "T+1".
23 | 2027-05-31 | 2027-06-03 | Schedule | T2 Synchronised Standard Day
23 | 2027-06-02 | 2027-06-02 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
23 | 2027-06-03 | 2027-06-03 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
23 | 2027-06-04 | 2027-06-04 | Release deployment | T2 R2027.JUN deployment (Package 13) | Critical RD only
23 | 2027-06-04 | 2027-06-04 | Schedule | T2 Synchronised Release Day
24 | 2027-06-07 | 2027-06-10 | Schedule | T2 Synchronised Standard Day
24 | 2027-06-09 | 2027-06-09 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
24 | 2027-06-10 | 2027-06-10 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
24 | 2027-06-11 | 2027-06-11 | Schedule | T2 Synchronised Release Day
25 | 2027-06-14 | 2027-06-17 | Schedule | T2 Synchronised Standard Day
25 | 2027-06-16 | 2027-06-16 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
25 | 2027-06-17 | 2027-06-17 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
25 | 2027-06-18 | 2027-06-18 | Schedule | T2 Synchronised Release Day
26 | 2027-06-21 | 2027-06-24 | Schedule | T2 Synchronised Standard Day
26 | 2027-06-23 | 2027-06-23 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
26 | 2027-06-24 | 2027-06-24 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
26 | 2027-06-25 | 2027-06-25 | Schedule | T2 Synchronised Release Day
27 | 2027-06-28 | 2027-07-01 | Schedule | T2 Live Timing Day | Approved accross WGs upon OMG request : "T+1".
27 | 2027-06-30 | 2027-06-30 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
27 | 2027-07-01 | 2027-07-01 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
27 | 2027-07-02 | 2027-07-02 | Schedule | T2 Live Timing Day | Approved accross WGs upon OMG request : "T+1".
28 | 2027-07-05 | 2027-07-08 | Schedule | T2 Live Timing Day | Approved accross WGs upon OMG request : "T+1".
28 | 2027-07-07 | 2027-07-07 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
28 | 2027-07-08 | 2027-07-08 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
28 | 2027-07-09 | 2027-07-09 | Schedule | T2 Live Timing Day | Approved accross WGs upon OMG request : "T+1".
29 | 2027-07-12 | 2027-07-15 | Schedule | T2 Synchronised Standard Day
29 | 2027-07-14 | 2027-07-14 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
29 | 2027-07-15 | 2027-07-15 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
29 | 2027-07-16 | 2027-07-16 | Schedule | T2 Synchronised Release Day
30 | 2027-07-19 | 2027-07-22 | Schedule | T2 Synchronised Standard Day
30 | 2027-07-21 | 2027-07-21 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
30 | 2027-07-22 | 2027-07-22 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
30 | 2027-07-23 | 2027-07-23 | Schedule | T2 Synchronised Release Day
31 | 2027-07-26 | 2027-07-29 | Schedule | T2 Synchronised Standard Day
31 | 2027-07-28 | 2027-07-28 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
31 | 2027-07-29 | 2027-07-29 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
31 | 2027-07-30 | 2027-07-30 | Schedule | T2 Synchronised Release Day
32 | 2027-08-02 | 2027-08-05 | Schedule | T2 Synchronised Standard Day
32 | 2027-08-04 | 2027-08-04 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
32 | 2027-08-05 | 2027-08-05 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
32 | 2027-08-06 | 2027-08-06 | Schedule | T2 Synchronised Release Day
33 | 2027-08-09 | 2027-08-12 | Schedule | T2 Synchronised Standard Day
33 | 2027-08-11 | 2027-08-11 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
33 | 2027-08-12 | 2027-08-12 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
33 | 2027-08-13 | 2027-08-13 | Schedule | T2 Synchronised Release Day
34 | 2027-08-16 | 2027-08-19 | Schedule | T2 Synchronised Standard Day
34 | 2027-08-18 | 2027-08-18 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
34 | 2027-08-19 | 2027-08-19 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
34 | 2027-08-20 | 2027-08-20 | Schedule | T2 Synchronised Release Day
35 | 2027-08-23 | 2027-08-26 | Schedule | T2 Live Timing Day | Approved accross WGs upon OMG request : "T+1".
35 | 2027-08-25 | 2027-08-25 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
35 | 2027-08-26 | 2027-08-26 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
35 | 2027-08-27 | 2027-08-27 | Schedule | T2 Synchronised Release Day
36 | 2027-08-30 | 2027-09-02 | Schedule | T2 Live Timing Day | Approved accross WGs upon OMG request : "T+1".
36 | 2027-09-01 | 2027-09-01 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
36 | 2027-09-02 | 2027-09-02 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
36 | 2027-09-03 | 2027-09-03 | Schedule | T2 Synchronised Release Day
37 | 2027-09-06 | 2027-09-09 | Schedule | T2 Live Timing Day | Approved accross WGs upon OMG request : "T+1".
37 | 2027-09-08 | 2027-09-08 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
37 | 2027-09-09 | 2027-09-09 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
37 | 2027-09-10 | 2027-09-10 | Schedule | T2 Synchronised Release Day
38 | 2027-09-13 | 2027-09-16 | Schedule | T2 Synchronised Standard Day
38 | 2027-09-15 | 2027-09-15 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
38 | 2027-09-16 | 2027-09-16 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
38 | 2027-09-17 | 2027-09-17 | Schedule | T2 Synchronised Release Day
39 | 2027-09-20 | 2027-09-23 | Schedule | T2 Synchronised Standard Day
39 | 2027-09-22 | 2027-09-22 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
39 | 2027-09-23 | 2027-09-23 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
39 | 2027-09-24 | 2027-09-24 | Schedule | T2 Synchronised Release Day
40 | 2027-09-27 | 2027-09-30 | Schedule | T2 Synchronised Standard Day
40 | 2027-09-29 | 2027-09-29 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
40 | 2027-09-30 | 2027-09-30 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
40 | 2027-10-01 | 2027-10-01 | Schedule | T2 Synchronised Release Day
41 | 2027-10-04 | 2027-10-07 | Schedule | T2 Synchronised Standard Day
41 | 2027-10-06 | 2027-10-06 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
41 | 2027-10-07 | 2027-10-07 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
41 | 2027-10-08 | 2027-10-08 | Schedule | T2 Synchronised Release Day
42 | 2027-10-11 | 2027-10-14 | Schedule | T2 Synchronised Standard Day
42 | 2027-10-13 | 2027-10-13 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
42 | 2027-10-14 | 2027-10-14 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
42 | 2027-10-15 | 2027-10-15 | Schedule | T2 Synchronised Release Day
43 | 2027-10-18 | 2027-10-21 | Schedule | T2 Synchronised Standard Day
43 | 2027-10-20 | 2027-10-20 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
43 | 2027-10-21 | 2027-10-21 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
43 | 2027-10-22 | 2027-10-22 | Schedule | T2 Synchronised Release Day
44 | 2027-10-25 | 2027-10-28 | Schedule | T2 Synchronised Standard Day
44 | 2027-10-27 | 2027-10-27 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
44 | 2027-10-28 | 2027-10-28 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
44 | 2027-10-29 | 2027-10-29 | Schedule | T2 Synchronised Release Day
45 | 2027-11-01 | 2027-11-04 | Schedule | T2 Synchronised Standard Day
45 | 2027-11-03 | 2027-11-03 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
45 | 2027-11-04 | 2027-11-04 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
45 | 2027-11-05 | 2027-11-05 | Schedule | T2 Synchronised Release Day
46 | 2027-11-08 | 2027-11-11 | Schedule | T2 Synchronised Standard Day
46 | 2027-11-10 | 2027-11-10 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
46 | 2027-11-11 | 2027-11-11 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
46 | 2027-11-12 | 2027-11-12 | Schedule | T2 Synchronised Release Day
47 | 2027-11-15 | 2027-11-18 | Schedule | T2 Synchronised Standard Day
47 | 2027-11-17 | 2027-11-17 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
47 | 2027-11-18 | 2027-11-18 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
47 | 2027-11-19 | 2027-11-19 | Schedule | T2 Synchronised Release Day
48 | 2027-11-22 | 2027-11-25 | Schedule | T2 Synchronised Standard Day
48 | 2027-11-24 | 2027-11-24 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
48 | 2027-11-25 | 2027-11-25 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
48 | 2027-11-26 | 2027-11-26 | Schedule | T2 Synchronised Release Day
49 | 2027-11-29 | 2027-12-02 | Schedule | T2 Synchronised Standard Day
49 | 2027-12-01 | 2027-12-01 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
49 | 2027-12-02 | 2027-12-02 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
49 | 2027-12-03 | 2027-12-03 | Schedule | T2 Synchronised Release Day
50 | 2027-12-06 | 2027-12-09 | Schedule | T2 Synchronised Standard Day
50 | 2027-12-08 | 2027-12-08 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
50 | 2027-12-09 | 2027-12-09 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
50 | 2027-12-10 | 2027-12-10 | Schedule | T2 Synchronised Release Day
51 | 2027-12-13 | 2027-12-16 | Schedule | T2 Synchronised Standard Day
51 | 2027-12-15 | 2027-12-15 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
51 | 2027-12-16 | 2027-12-16 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
51 | 2027-12-17 | 2027-12-17 | Schedule | T2 Synchronised Release Day
52 | 2027-12-20 | 2027-12-23 | Schedule | T2 Synchronised Standard Day
52 | 2027-12-22 | 2027-12-22 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
52 | 2027-12-23 | 2027-12-23 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
52 | 2027-12-24 | 2027-12-24 | Schedule | T2 Closing Day | Christmas
1 | 2027-12-27 | 2027-12-30 | Schedule | T2 Synchronised Standard Day
1 | 2027-12-29 | 2027-12-29 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
1 | 2027-12-30 | 2027-12-30 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
1 | 2027-12-31 | 2027-12-31 | Schedule | T2 Closing Day | Christmas