## Calendar external
Week number | Start Date | End Date | Activity type | Activities | Comments
45 | 2025-11-03 | 2025-11-05 | Release testing | T2 R2025.NOV release testing in Pre-Production
45 | 2025-11-03 | 2025-11-06 | Schedule | T2 Synchronised Standard day
45 | 2025-11-05 | 2025-11-05 | Special testing | BILL invoice for NCBs | Billing period 27/10/-31/10/2025
45 | 2025-11-05 | 2025-11-05 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
45 | 2025-11-05 | 2025-11-05 | Release testing | End of testing of T2 R2025.NOV scope elements in Pre-Production
45 | 2025-11-05 | 2025-11-05 | Special testing | Open ECONSII from 10:00 - 12:00 CET
45 | 2025-11-06 | 2025-11-06 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
45 | 2025-11-07 | 2025-11-07 | Release deployment | T2 R2025.NOV deployment (Package 12) | critical RDs only / Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
45 | 2025-11-07 | 2025-11-07 | Schedule | T2 Synchronised Release day
46 | 2025-11-10 | 2025-11-12 | Schedule | T2 Synchronised Standard day
46 | 2025-11-12 | 2025-11-12 | Special testing | Open ECONSII from 09:00 - 14:00 CET | to support DECB & FRCB ECONSII regular testing
46 | 2025-11-12 | 2025-11-12 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
46 | 2025-11-12 | 2025-11-12 | Special testing | BILL invoice for NCBs | Billing period 01/11/-09/11/2025
46 | 2025-11-13 | 2025-11-13 | Schedule | T2 Live Timing | To support FRCB testing activities for T2 community
46 | 2025-11-13 | 2025-11-13 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
46 | 2025-11-14 | 2025-11-14 | Migration testing | Bulgaria Euro adoption migration test 2 | no impact on other testing activities
46 | 2025-11-14 | 2025-11-14 | Schedule | T2 Synchronised Release day
47 | 2025-11-17 | 2025-11-20 | Schedule | T2 Synchronised Standard day
47 | 2025-11-18 | 2025-11-18 | Migration testing | Bulgaria Euro adoption migration test 2 | no impact on other testing activities
47 | 2025-11-19 | 2025-11-19 | Special testing | Open ECONSII from 10:00 - 12:00 CET
47 | 2025-11-19 | 2025-11-19 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
47 | 2025-11-20 | 2025-11-20 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
47 | 2025-11-21 | 2025-11-21 | Schedule | T2 Synchronised Release day
48 | 2025-11-24 | 2025-11-27 | Schedule | T2 Synchronised Standard day
48 | 2025-11-26 | 2025-11-26 | Special testing | Open ECONSII from 10:00 - 12:00 CET
48 | 2025-11-26 | 2025-11-26 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
48 | 2025-11-27 | 2025-11-27 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
48 | 2025-11-28 | 2025-11-28 | Schedule | T2 Synchronised Release day
49 | 2025-12-01 | 2025-12-04 | Schedule | T2 Synchronised Standard day
49 | 2025-12-03 | 2025-12-03 | Special testing | BILL invoice for NCBs | Billing period 10/11/-30/11/2025
49 | 2025-12-03 | 2025-12-03 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
49 | 2025-12-03 | 2025-12-03 | Special testing | Open ECONSII from 10:00 - 12:00 CET
49 | 2025-12-04 | 2025-12-04 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
49 | 2025-12-05 | 2025-12-05 | Schedule | T2 Synchronised Release day
50 | 2025-12-08 | 2025-12-11 | Schedule | T2 Synchronised Standard day
50 | 2025-12-10 | 2025-12-10 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
50 | 2025-12-10 | 2025-12-10 | ORT | T2S ORT "RAD Tests (Inter regional failover with loss of data)" with impact on T2 | Impact on T2: a snapshot of the system will be taken during the evening before the test and reloaded the day after in the morning. All the updates performed in the system (UTEST), included CoCo, will be lost.
50 | 2025-12-10 | 2025-12-10 | Special testing | Open ECONSII from 10:00 - 12:00 CET
50 | 2025-12-11 | 2025-12-11 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
50 | 2025-12-12 | 2025-12-12 | Schedule | T2 Synchronised Release day
51 | 2025-12-15 | 2025-12-18 | Schedule | T2 Synchronised Standard day
51 | 2025-12-17 | 2025-12-17 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
51 | 2025-12-17 | 2025-12-17 | Special testing | Open ECONSII from 10:00 - 12:00 CET
51 | 2025-12-18 | 2025-12-18 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
51 | 2025-12-19 | 2025-12-19 | Schedule | T2 Synchronised Release day
52 | 2025-12-22 | 2025-12-23 | Schedule | T2 Synchronised Standard day
52 | 2025-12-24 | 2025-12-24 | Schedule | T2 closing day | Christmas Eve
52 | 2025-12-25 | 2025-12-25 | Schedule | T2 closing day | Christmas Day
52 | 2025-12-26 | 2025-12-26 | Schedule | T2 closing day | Boxing Day
1 | 2025-12-29 | 2025-12-30 | Schedule | T2 Synchronised Standard day
53 | 2025-12-30 | 2025-12-30 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
1 | 2025-12-31 | 2025-12-31 | Schedule | T2 closing day | New Year's Eve
1 | 2026-01-01 | 2026-01-01 | Schedule | T2 closing day
1 | 2026-01-02 | 2026-01-02 | Schedule | T2 Synchronised Release day
2 | 2026-01-06 | 2026-01-06 | Special testing | BILL invoice for NCBs | Billing period 01/12/-31/12/2025
11 | 2026-03-12 | 2026-03-12 | Reporting | Service Transition Status Report (STSR) for T2 R2026.JUN in Pre-Production (cut-off and delivery T2-WG)
11 | 2026-03-13 | 2026-03-13 | Reporting | T2-WG Go / No-go decision to deploy T2 R2026.JUN to Pre-Production | 8 business days before UTEST deployment
13 | 2026-03-27 | 2026-03-27 | Release deployment | T2 R2026.JUN deployment to Pre-Production (Packages 1-8) | Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
14 | 2026-03-30 | 2026-03-30 | Release testing | Start of testing of T2 R2026.JUN scope elements in Pre-Production
14 | 2026-03-30 | 2026-04-03 | Release testing | T2 R2026.JUN release testing in Pre-Production
15 | 2026-04-06 | 2026-04-10 | Release testing | T2 R2026.JUN release testing in Pre-Production
16 | 2026-04-13 | 2026-04-17 | Release testing | T2 R2026.JUN release testing in Pre-Production
16 | 2026-04-17 | 2026-04-17 | Release deployment | T2 R2026.JUN deployment (Package 9) | RD only Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
17 | 2026-04-20 | 2026-04-24 | Release testing | T2 R2026.JUN release testing in Pre-Production
17 | 2026-04-24 | 2026-04-24 | Release deployment | T2 R2026.JUN deployment (Package 10) | RD only Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
18 | 2026-04-27 | 2026-05-01 | Release testing | T2 R2026.JUN release testing in Pre-Production
18 | 2026-04-30 | 2026-04-30 | Release deployment | T2 R2026.JUN deployment (Package 11) | RD only Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
19 | 2026-05-04 | 2026-05-08 | Release testing | T2 R2026.JUN release testing in Pre-Production
19 | 2026-05-07 | 2026-05-07 | Release deployment | T2 R2026.JUN deployment (Package 12) | RD only Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
20 | 2026-05-11 | 2026-05-15 | Release testing | T2 R2026.JUN release testing in Pre-Production
20 | 2026-05-13 | 2026-05-13 | Release deployment | T2 R2026.JUN deployment (Package 13) | Critical RD only Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
21 | 2026-05-18 | 2026-05-22 | Release testing | T2 R2026.JUN release testing in Pre-Production
21 | 2026-05-22 | 2026-05-22 | Release deployment | T2 R2026.JUN deployment (Package 14) | Critical RD only Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
22 | 2026-05-25 | 2026-05-27 | Release testing | T2 R2026.JUN release testing in Pre-Production
22 | 2026-05-27 | 2026-05-27 | Release testing | End of testing of T2 R2026.JUN scope elements in Pre-Production
22 | 2026-05-29 | 2026-05-29 | Release deployment | T2 R2026.JUN deployment (Package 15) | Critical RD only Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
23 | 2026-06-05 | 2026-06-05 | Release deployment | T2 R2026.JUN deployment (Package 16) | Critical RD only Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
38 | 2026-09-15 | 2026-09-15 | Reporting | T2-WG Go / No-go decision to deploy T2 R2026.NOV to Pre-Production
39 | 2026-09-25 | 2026-09-25 | Release deployment | T2 R2026.NOV deployment to Pre-Production (Packages 1-6)
40 | 2026-10-02 | 2026-10-02 | Release deployment | T2 R2026.NOV deployment (Package 7) | RD only
41 | 2026-10-09 | 2026-10-09 | Release deployment | T2 R2026.NOV deployment (Package 8) | RD only
42 | 2026-10-16 | 2026-10-16 | Release deployment | T2 R2026.NOV deployment (Package 9) | critical RD only
43 | 2026-10-23 | 2026-10-23 | Release deployment | T2 R2026.NOV deployment (Package 10) | critical RD only
44 | 2026-10-30 | 2026-10-30 | Release deployment | T2 R2026.NOV deployment (Package 11) | critical RD only
45 | 2026-11-06 | 2026-11-06 | Release deployment | T2 R2026.NOV deployment (Package 12) | critical RD only