## Calendar external
Week number | Start Date | End Date | Activity type | Activities | Comments
46 | 2025-11-10 | 2025-11-12 | Schedule | T2 Synchronised Standard day
46 | 2025-11-12 | 2025-11-12 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
46 | 2025-11-12 | 2025-11-12 | Special testing | BILL invoice for NCBs | Billing period 01/11/-09/11/2025
46 | 2025-11-12 | 2025-11-12 | Special testing | Open ECONSII from 09:00 - 14:00 CET | to support DECB & FRCB ECONSII regular testing
46 | 2025-11-13 | 2025-11-13 | Schedule | T2 Live Timing | To support FRCB testing activities for T2 community
46 | 2025-11-13 | 2025-11-13 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
46 | 2025-11-14 | 2025-11-14 | Operational activity | T2 hot fix deployment (PBI237222) | PROD deployment scheduled 29/11/2025 CoCo PBI (also OMG approved)
46 | 2025-11-14 | 2025-11-14 | Migration testing | Bulgaria Euro adoption migration test 2 | no impact on other testing activities
46 | 2025-11-14 | 2025-11-14 | Schedule | T2 Synchronised Release day
47 | 2025-11-17 | 2025-11-20 | Schedule | T2 Synchronised Standard day
47 | 2025-11-18 | 2025-11-18 | Migration testing | Bulgaria Euro adoption migration test 2 | no impact on other testing activities
47 | 2025-11-19 | 2025-11-19 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
47 | 2025-11-19 | 2025-11-19 | Special testing | Open ECONSII from 10:00 - 12:00 CET
47 | 2025-11-19 | 2025-11-19 | Special testing | BILL invoice for NCBs | Billing period 10/11/-16/11/2025
47 | 2025-11-20 | 2025-11-20 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
47 | 2025-11-21 | 2025-11-21 | Schedule | T2 Synchronised Release day
48 | 2025-11-24 | 2025-11-27 | Schedule | T2 Synchronised Standard day
48 | 2025-11-26 | 2025-11-26 | Special testing | BILL invoice for NCBs | Billing period 17/11/-23/11/2025
48 | 2025-11-26 | 2025-11-26 | Special testing | Open ECONSII from 10:00 - 12:00 CET
48 | 2025-11-26 | 2025-11-26 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
48 | 2025-11-27 | 2025-11-27 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
48 | 2025-11-28 | 2025-11-28 | Schedule | T2 Synchronised Release day
49 | 2025-12-01 | 2025-12-04 | Schedule | T2 Synchronised Standard day
49 | 2025-12-03 | 2025-12-03 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
49 | 2025-12-03 | 2025-12-03 | Special testing | Open ECONSII from 10:00 - 12:00 CET
49 | 2025-12-03 | 2025-12-03 | Special testing | BILL invoice for NCBs | Billing period 24/11/-30/11/2025
49 | 2025-12-04 | 2025-12-04 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
49 | 2025-12-05 | 2025-12-05 | Schedule | T2 Synchronised Release day
50 | 2025-12-08 | 2025-12-11 | Schedule | T2 Synchronised Standard day
50 | 2025-12-10 | 2025-12-10 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
50 | 2025-12-10 | 2025-12-10 | ORT | T2S ORT "RAD Tests (Inter regional failover with loss of data)" with impact on T2 | Impact on T2: a snapshot of the system will be taken during the evening before the test and reloaded the day after in the morning. All the updates performed in the system (UTEST), included CoCo, will be lost.
50 | 2025-12-10 | 2025-12-10 | Special testing | Open ECONSII from 10:00 - 12:00 CET
50 | 2025-12-11 | 2025-12-11 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
50 | 2025-12-12 | 2025-12-12 | Schedule | T2 Synchronised Release day
51 | 2025-12-15 | 2025-12-18 | Schedule | T2 Synchronised Standard day
51 | 2025-12-17 | 2025-12-17 | Special testing | Open ECONSII from 10:00 - 12:00 CET
51 | 2025-12-17 | 2025-12-17 | Special testing | Start of new maintenance period for minimum reserves (weekly period)
51 | 2025-12-18 | 2025-12-18 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
51 | 2025-12-19 | 2025-12-19 | Schedule | T2 Synchronised Release day
52 | 2025-12-22 | 2025-12-23 | Schedule | T2 Synchronised Standard day
52 | 2025-12-24 | 2025-12-24 | Schedule | T2 closing day | Christmas Eve
52 | 2025-12-25 | 2025-12-25 | Schedule | T2 closing day | Christmas Day
52 | 2025-12-26 | 2025-12-26 | Schedule | T2 closing day | Boxing Day
1 | 2025-12-29 | 2025-12-30 | Schedule | T2 Synchronised Standard day
53 | 2025-12-30 | 2025-12-30 | Special testing | Settlement of interest for (excess of) minimum reserves for previous maintenance period
1 | 2025-12-31 | 2025-12-31 | Schedule | T2 closing day | New Year's Eve
1 | 2026-01-01 | 2026-01-01 | Schedule | T2 closing day
1 | 2026-01-02 | 2026-01-02 | Schedule | T2 Synchronised Release day
2 | 2026-01-05 | 2026-01-08 | Schedule | T2 Synchronised Standard day
2 | 2026-01-06 | 2026-01-06 | Special testing | BILL invoice for NCBs | Billing period 01/12/-31/12/2025
2 | 2026-01-07 | 2026-01-07 | Special testing | Open ECONSII from 10:00 - 12:00 CET
2 | 2026-01-09 | 2026-01-09 | Schedule | T2 Synchronised Release day
3 | 2026-01-12 | 2026-01-15 | Schedule | T2 Synchronised Standard day
3 | 2026-01-14 | 2026-01-14 | Special testing | Open ECONSII from 10:00 - 12:00 CET
3 | 2026-01-16 | 2026-01-16 | Schedule | T2 Synchronised Release day
4 | 2026-01-19 | 2026-01-22 | Schedule | T2 Synchronised Standard day
4 | 2026-01-21 | 2026-01-21 | Special testing | Open ECONSII from 10:00 - 12:00 CET
4 | 2026-01-23 | 2026-01-23 | Schedule | T2 Synchronised Release day
5 | 2026-01-26 | 2026-01-29 | Schedule | T2 Synchronised Standard day
5 | 2026-01-28 | 2026-01-28 | Special testing | Open ECONSII from 10:00 - 12:00 CET
5 | 2026-01-30 | 2026-01-30 | Schedule | T2 Synchronised Release day
6 | 2026-02-02 | 2026-02-05 | Schedule | T2 Synchronised Standard day
6 | 2026-02-04 | 2026-02-04 | Special testing | BILL invoice for NCBs | Billing period 01/01/2026-31/01/2026
6 | 2026-02-04 | 2026-02-04 | Special testing | Open ECONSII from 10:00 - 12:00 CET
6 | 2026-02-06 | 2026-02-06 | Schedule | T2 Synchronised Release day
7 | 2026-02-09 | 2026-02-12 | Schedule | T2 Synchronised Standard day
7 | 2026-02-11 | 2026-02-11 | Special testing | Open ECONSII from 10:00 - 12:00 CET
7 | 2026-02-13 | 2026-02-13 | Schedule | T2 Synchronised Release day
8 | 2026-02-16 | 2026-02-19 | Schedule | T2 Synchronised Standard day
8 | 2026-02-18 | 2026-02-18 | Special testing | Open ECONSII from 10:00 - 12:00 CET
8 | 2026-02-20 | 2026-02-20 | Schedule | T2 Synchronised Release day
9 | 2026-02-23 | 2026-02-26 | Schedule | T2 Synchronised Standard day
9 | 2026-02-25 | 2026-02-25 | Special testing | Open ECONSII from 10:00 - 12:00 CET
9 | 2026-02-27 | 2026-02-27 | Schedule | T2 Synchronised Release day
10 | 2026-03-02 | 2026-03-05 | Schedule | T2 Synchronised Standard day
10 | 2026-03-04 | 2026-03-04 | Special testing | BILL invoice for NCBs | Billing period 01/02/-28/02/2026
10 | 2026-03-04 | 2026-03-04 | Special testing | Open ECONSII from 10:00 - 12:00 CET
10 | 2026-03-06 | 2026-03-06 | Schedule | T2 Synchronised Release day
11 | 2026-03-09 | 2026-03-12 | Schedule | T2 Synchronised Standard day
11 | 2026-03-11 | 2026-03-11 | Special testing | Open ECONSII from 10:00 - 12:00 CET
11 | 2026-03-12 | 2026-03-12 | Reporting | Service Transition Status Report (STSR) for T2 R2026.JUN in Pre-Production (cut-off and delivery T2-WG)
11 | 2026-03-13 | 2026-03-13 | Reporting | T2-WG Go / No-go decision to deploy T2 R2026.JUN to Pre-Production | 8 business days before UTEST deployment
11 | 2026-03-13 | 2026-03-13 | Schedule | T2 Synchronised Release day
12 | 2026-03-16 | 2026-03-19 | Schedule | T2 Synchronised Standard day
12 | 2026-03-18 | 2026-03-18 | Special testing | Open ECONSII from 10:00 - 12:00 CET
12 | 2026-03-20 | 2026-03-20 | Schedule | T2 Synchronised Release day
13 | 2026-03-23 | 2026-03-26 | Schedule | T2 Synchronised Standard day
13 | 2026-03-25 | 2026-03-25 | Special testing | Open ECONSII from 10:00 - 12:00 CET
13 | 2026-03-27 | 2026-03-27 | Schedule | T2 Synchronised Release day
13 | 2026-03-27 | 2026-03-27 | Release deployment | T2 R2026.JUN deployment to Pre-Production (Packages 1-8) | Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
14 | 2026-03-30 | 2026-03-30 | Release testing | Start of testing of T2 R2026.JUN scope elements in Pre-Production
14 | 2026-03-30 | 2026-04-02 | Schedule | T2 Synchronised Standard day
14 | 2026-03-30 | 2026-04-03 | Release testing | T2 R2026.JUN release testing in Pre-Production
14 | 2026-04-01 | 2026-04-01 | Special testing | Open ECONSII from 10:00 - 12:00 CET
14 | 2026-04-03 | 2026-04-03 | Schedule | T2 closing day
15 | 2026-04-06 | 2026-04-06 | Schedule | T2 closing day
15 | 2026-04-06 | 2026-04-10 | Release testing | T2 R2026.JUN release testing in Pre-Production
15 | 2026-04-07 | 2026-04-07 | Special testing | BILL invoice for NCBs | Billing period 01/03/-31/03/2026
15 | 2026-04-07 | 2026-04-09 | Schedule | T2 Synchronised Standard day
15 | 2026-04-08 | 2026-04-08 | Special testing | Open ECONSII from 10:00 - 12:00 CET
15 | 2026-04-10 | 2026-04-10 | Schedule | T2 Synchronised Release day
16 | 2026-04-13 | 2026-04-16 | Schedule | T2 Synchronised Standard day
16 | 2026-04-13 | 2026-04-17 | Release testing | T2 R2026.JUN release testing in Pre-Production
16 | 2026-04-15 | 2026-04-15 | Special testing | Open ECONSII from 10:00 - 12:00 CET
16 | 2026-04-17 | 2026-04-17 | Release deployment | T2 R2026.JUN deployment (Package 9) | RD only Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
16 | 2026-04-17 | 2026-04-17 | Schedule | T2 Synchronised Release day
17 | 2026-04-20 | 2026-04-23 | Schedule | T2 Synchronised Standard day
17 | 2026-04-20 | 2026-04-24 | Release testing | T2 R2026.JUN release testing in Pre-Production
17 | 2026-04-22 | 2026-04-22 | Special testing | Open ECONSII from 10:00 - 12:00 CET
17 | 2026-04-24 | 2026-04-24 | Release deployment | T2 R2026.JUN deployment (Package 10) | RD only Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
17 | 2026-04-24 | 2026-04-24 | Schedule | T2 Synchronised Release day
18 | 2026-04-27 | 2026-04-29 | Schedule | T2 Synchronised Standard day
18 | 2026-04-27 | 2026-05-01 | Release testing | T2 R2026.JUN release testing in Pre-Production
18 | 2026-04-29 | 2026-04-29 | Special testing | Open ECONSII from 10:00 - 12:00 CET
18 | 2026-04-30 | 2026-04-30 | Release deployment | T2 R2026.JUN deployment (Package 11) | RD only Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
18 | 2026-04-30 | 2026-04-30 | Schedule | T2 Synchronised Release day
18 | 2026-05-01 | 2026-05-01 | Schedule | T2 closing day
19 | 2026-05-04 | 2026-05-07 | Schedule | T2 Synchronised Standard day
19 | 2026-05-04 | 2026-05-08 | Release testing | T2 R2026.JUN release testing in Pre-Production
19 | 2026-05-06 | 2026-05-06 | Special testing | BILL invoice for NCBs | Billing period 01/04/-30/04/2026
19 | 2026-05-06 | 2026-05-06 | Special testing | Open ECONSII from 10:00 - 12:00 CET
19 | 2026-05-07 | 2026-05-07 | Release deployment | T2 R2026.JUN deployment (Package 12) | RD only Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
19 | 2026-05-08 | 2026-05-08 | Schedule | T2 Synchronised Release day
20 | 2026-05-11 | 2026-05-14 | Schedule | T2 Synchronised Standard day
20 | 2026-05-11 | 2026-05-15 | Release testing | T2 R2026.JUN release testing in Pre-Production
20 | 2026-05-13 | 2026-05-13 | Release deployment | T2 R2026.JUN deployment (Package 13) | Critical RD only Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
20 | 2026-05-13 | 2026-05-13 | Special testing | Open ECONSII from 10:00 - 12:00 CET
20 | 2026-05-15 | 2026-05-15 | Schedule | T2 Synchronised Release day
21 | 2026-05-18 | 2026-05-21 | Schedule | T2 Synchronised Standard day
21 | 2026-05-18 | 2026-05-22 | Release testing | T2 R2026.JUN release testing in Pre-Production
21 | 2026-05-20 | 2026-05-20 | Special testing | Open ECONSII from 10:00 - 12:00 CET
21 | 2026-05-22 | 2026-05-22 | Release deployment | T2 R2026.JUN deployment (Package 14) | Critical RD only Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
21 | 2026-05-22 | 2026-05-22 | Schedule | T2 Synchronised Release day
22 | 2026-05-25 | 2026-05-27 | Release testing | T2 R2026.JUN release testing in Pre-Production
22 | 2026-05-25 | 2026-05-28 | Schedule | T2 Synchronised Standard day
22 | 2026-05-27 | 2026-05-27 | Special testing | Open ECONSII from 10:00 - 12:00 CET
22 | 2026-05-27 | 2026-05-27 | Release testing | End of testing of T2 R2026.JUN scope elements in Pre-Production
22 | 2026-05-29 | 2026-05-29 | Release deployment | T2 R2026.JUN deployment (Package 15) | Critical RD only Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
22 | 2026-05-29 | 2026-05-29 | Schedule | T2 Synchronised Release day
23 | 2026-06-01 | 2026-06-04 | Schedule | T2 Synchronised Standard day
23 | 2026-06-03 | 2026-06-03 | Special testing | BILL invoice for NCBs | Billing period 01/05/-31/05/2026
23 | 2026-06-03 | 2026-06-03 | Special testing | Open ECONSII from 10:00 - 12:00 CET
23 | 2026-06-05 | 2026-06-05 | Release deployment | T2 R2026.JUN deployment (Package 16) | Critical RD only Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
23 | 2026-06-05 | 2026-06-05 | Schedule | T2 Synchronised Release day
24 | 2026-06-08 | 2026-06-11 | Schedule | T2 Synchronised Standard day
24 | 2026-06-10 | 2026-06-10 | Special testing | Open ECONSII from 10:00 - 12:00 CET
24 | 2026-06-12 | 2026-06-12 | Schedule | T2 Synchronised Release day
25 | 2026-06-15 | 2026-06-18 | Schedule | T2 Synchronised Standard day
25 | 2026-06-17 | 2026-06-17 | Special testing | Open ECONSII from 10:00 - 12:00 CET
25 | 2026-06-19 | 2026-06-19 | Schedule | T2 Synchronised Release day
26 | 2026-06-22 | 2026-06-25 | Schedule | T2 Synchronised Standard day
26 | 2026-06-24 | 2026-06-24 | Special testing | Open ECONSII from 10:00 - 12:00 CET
26 | 2026-06-26 | 2026-06-26 | Schedule | T2 Synchronised Release day
27 | 2026-06-29 | 2026-07-02 | Schedule | T2 Synchronised Standard day
27 | 2026-07-01 | 2026-07-01 | Special testing | Open ECONSII from 10:00 - 12:00 CET
27 | 2026-07-03 | 2026-07-03 | Special testing | BILL invoice for NCBs | Billing period 01/06/-30/06/2026
27 | 2026-07-03 | 2026-07-03 | Schedule | T2 Synchronised Release day
28 | 2026-07-06 | 2026-07-09 | Schedule | T2 Synchronised Standard day
28 | 2026-07-08 | 2026-07-08 | Special testing | Open ECONSII from 10:00 - 12:00 CET
28 | 2026-07-10 | 2026-07-10 | Schedule | T2 Synchronised Release day
29 | 2026-07-13 | 2026-07-16 | Schedule | T2 Synchronised Standard day
29 | 2026-07-15 | 2026-07-15 | Special testing | Open ECONSII from 10:00 - 12:00 CET
29 | 2026-07-17 | 2026-07-17 | Schedule | T2 Synchronised Release day
30 | 2026-07-20 | 2026-07-23 | Schedule | T2 Synchronised Standard day
30 | 2026-07-22 | 2026-07-22 | Special testing | Open ECONSII from 10:00 - 12:00 CET
30 | 2026-07-24 | 2026-07-24 | Schedule | T2 Synchronised Release day
31 | 2026-07-27 | 2026-07-30 | Schedule | T2 Synchronised Standard day
31 | 2026-07-29 | 2026-07-29 | Special testing | Open ECONSII from 10:00 - 12:00 CET
31 | 2026-07-31 | 2026-07-31 | Schedule | T2 Synchronised Release day
32 | 2026-08-03 | 2026-08-06 | Schedule | T2 Synchronised Standard day
32 | 2026-08-05 | 2026-08-05 | Special testing | BILL invoice for NCBs | Billing period 01/07/-31/07/2026
32 | 2026-08-05 | 2026-08-05 | Special testing | Open ECONSII from 10:00 - 12:00 CET
32 | 2026-08-07 | 2026-08-07 | Schedule | T2 Synchronised Release day
33 | 2026-08-10 | 2026-08-13 | Schedule | T2 Synchronised Standard day
33 | 2026-08-12 | 2026-08-12 | Special testing | Open ECONSII from 10:00 - 12:00 CET
33 | 2026-08-14 | 2026-08-14 | Schedule | T2 Synchronised Release day
34 | 2026-08-17 | 2026-08-20 | Schedule | T2 Synchronised Standard day
34 | 2026-08-19 | 2026-08-19 | Special testing | Open ECONSII from 10:00 - 12:00 CET
34 | 2026-08-21 | 2026-08-21 | Schedule | T2 Synchronised Release day
35 | 2026-08-24 | 2026-08-27 | Schedule | T2 Synchronised Standard day
35 | 2026-08-26 | 2026-08-26 | Special testing | Open ECONSII from 10:00 - 12:00 CET
35 | 2026-08-28 | 2026-08-28 | Schedule | T2 Synchronised Release day
36 | 2026-08-31 | 2026-09-03 | Schedule | T2 Synchronised Standard day
36 | 2026-09-02 | 2026-09-02 | Special testing | Open ECONSII from 10:00 - 12:00 CET
36 | 2026-09-03 | 2026-09-03 | Special testing | BILL invoice for NCBs | Billing period 01/08/-31/08/2026
36 | 2026-09-04 | 2026-09-04 | Schedule | T2 Synchronised Release day
37 | 2026-09-07 | 2026-09-10 | Schedule | T2 Synchronised Standard day
37 | 2026-09-09 | 2026-09-09 | Special testing | Open ECONSII from 10:00 - 12:00 CET
37 | 2026-09-11 | 2026-09-11 | Schedule | T2 Synchronised Release day
38 | 2026-09-14 | 2026-09-17 | Schedule | T2 Synchronised Standard day
38 | 2026-09-15 | 2026-09-15 | Reporting | T2-WG Go / No-go decision to deploy T2 R2026.NOV to Pre-Production
38 | 2026-09-16 | 2026-09-16 | Special testing | Open ECONSII from 10:00 - 12:00 CET
38 | 2026-09-18 | 2026-09-18 | Schedule | T2 Synchronised Release day
39 | 2026-09-21 | 2026-09-24 | Schedule | T2 Synchronised Standard day
39 | 2026-09-23 | 2026-09-23 | Special testing | Open ECONSII from 10:00 - 12:00 CET
39 | 2026-09-25 | 2026-09-25 | Release deployment | T2 R2026.NOV deployment to Pre-Production (Packages 1-6)
39 | 2026-09-25 | 2026-09-25 | Schedule | T2 Synchronised Release day
40 | 2026-09-28 | 2026-10-01 | Schedule | T2 Synchronised Standard day
40 | 2026-09-30 | 2026-09-30 | Special testing | Open ECONSII from 10:00 - 12:00 CET
40 | 2026-10-02 | 2026-10-02 | Release deployment | T2 R2026.NOV deployment (Package 7) | RD only
40 | 2026-10-02 | 2026-10-02 | Schedule | T2 Synchronised Release day
41 | 2026-10-05 | 2026-10-05 | Special testing | BILL invoice for NCBs | Billing period 01/09/-30/09/2026
41 | 2026-10-05 | 2026-10-08 | Schedule | T2 Synchronised Standard day
41 | 2026-10-07 | 2026-10-07 | Special testing | Open ECONSII from 10:00 - 12:00 CET
41 | 2026-10-09 | 2026-10-09 | Release deployment | T2 R2026.NOV deployment (Package 8) | RD only
41 | 2026-10-09 | 2026-10-09 | Schedule | T2 Synchronised Release day
42 | 2026-10-12 | 2026-10-15 | Schedule | T2 Synchronised Standard day
42 | 2026-10-14 | 2026-10-14 | Special testing | Open ECONSII from 10:00 - 12:00 CET
42 | 2026-10-16 | 2026-10-16 | Release deployment | T2 R2026.NOV deployment (Package 9) | critical RD only
42 | 2026-10-16 | 2026-10-16 | Schedule | T2 Synchronised Release day
43 | 2026-10-19 | 2026-10-22 | Schedule | T2 Synchronised Standard day
43 | 2026-10-21 | 2026-10-21 | Special testing | Open ECONSII from 10:00 - 12:00 CET
43 | 2026-10-23 | 2026-10-23 | Release deployment | T2 R2026.NOV deployment (Package 10) | critical RD only
43 | 2026-10-23 | 2026-10-23 | Schedule | T2 Synchronised Release day
44 | 2026-10-26 | 2026-10-29 | Schedule | T2 Synchronised Standard day
44 | 2026-10-28 | 2026-10-28 | Special testing | Open ECONSII from 10:00 - 12:00 CET
44 | 2026-10-30 | 2026-10-30 | Release deployment | T2 R2026.NOV deployment (Package 11) | critical RD only
44 | 2026-10-30 | 2026-10-30 | Schedule | T2 Synchronised Release day
45 | 2026-11-02 | 2026-11-05 | Schedule | T2 Synchronised Standard day
45 | 2026-11-04 | 2026-11-04 | Special testing | BILL invoice for NCBs | Billing period 01/10/-31/10/2026
45 | 2026-11-04 | 2026-11-04 | Special testing | Open ECONSII from 10:00 - 12:00 CET
45 | 2026-11-06 | 2026-11-06 | Release deployment | T2 R2026.NOV deployment (Package 12) | critical RD only
45 | 2026-11-06 | 2026-11-06 | Schedule | T2 Synchronised Release day
46 | 2026-11-09 | 2026-11-12 | Schedule | T2 Synchronised Standard day
46 | 2026-11-11 | 2026-11-11 | Special testing | Open ECONSII from 10:00 - 12:00 CET
46 | 2026-11-13 | 2026-11-13 | Schedule | T2 Synchronised Release day
47 | 2026-11-16 | 2026-11-19 | Schedule | T2 Synchronised Standard day
47 | 2026-11-18 | 2026-11-18 | Special testing | Open ECONSII from 10:00 - 12:00 CET
47 | 2026-11-20 | 2026-11-20 | Schedule | T2 Synchronised Release day
48 | 2026-11-23 | 2026-11-26 | Schedule | T2 Synchronised Standard day
48 | 2026-11-25 | 2026-11-25 | Special testing | Open ECONSII from 10:00 - 12:00 CET
48 | 2026-11-27 | 2026-11-27 | Schedule | T2 Synchronised Release day
49 | 2026-11-30 | 2026-12-03 | Schedule | T2 Synchronised Standard day
49 | 2026-12-02 | 2026-12-02 | Special testing | Open ECONSII from 10:00 - 12:00 CET
49 | 2026-12-03 | 2026-12-03 | Special testing | BILL invoice for NCBs | Billing period 01/11/-30/11/2026
49 | 2026-12-04 | 2026-12-04 | Schedule | T2 Synchronised Release day
50 | 2026-12-07 | 2026-12-10 | Schedule | T2 Synchronised Standard day
50 | 2026-12-09 | 2026-12-09 | Special testing | Open ECONSII from 10:00 - 12:00 CET
50 | 2026-12-11 | 2026-12-11 | Schedule | T2 Synchronised Release day
51 | 2026-12-14 | 2026-12-17 | Schedule | T2 Synchronised Standard day
51 | 2026-12-16 | 2026-12-16 | Special testing | Open ECONSII from 10:00 - 12:00 CET
51 | 2026-12-18 | 2026-12-18 | Schedule | T2 Synchronised Release day
52 | 2026-12-21 | 2026-12-23 | Schedule | T2 Synchronised Standard day
52 | 2026-12-23 | 2026-12-23 | Special testing | Open ECONSII from 10:00 - 12:00 CET
52 | 2026-12-24 | 2026-12-24 | Schedule | T2 closing day
52 | 2026-12-25 | 2026-12-25 | Schedule | T2 closing day
1 | 2026-12-28 | 2026-12-30 | Schedule | T2 Synchronised Standard day
1 | 2026-12-31 | 2026-12-31 | Schedule | T2 closing day
1 | 2027-01-01 | 2027-01-01 | Schedule | T2 closing day
2 | 2027-01-06 | 2027-01-06 | Special testing | BILL invoice for NCBs | Billing period 01/12/-31/12/2026