## CBT-UT Calendar
Week number | Start Date | End Date | Activity type | Activity Name | Pending agreement | EAC | UTEST | PROD | Comments
41 | 2026-10-09 | 2026-11-11 | Release testing | [R2026.NOV] [TIPS] User Testing in UTEST |  |  | U
42 | 2026-10-16 | 2026-10-16 | Release deployment | [R2026.NOV] [TIPS] Deployment of further scoped elements and release defects in UTEST |  |  | U
43 | 2026-10-21 | 2026-10-21 | Special testing | BILL invoice for NCBs |  | E |  |  | Billing period 1-18 October
43 | 2026-10-21 | 2026-10-21 | Special testing | BILL invoice for NCBs |  |  | U |  | Billing period 1-18 October
43 | 2026-10-23 | 2026-10-23 | Release deployment | [R2026.NOV] [TIPS] Deployment of further scoped elements and release defects in UTEST |  |  | U
44 | 2026-10-30 | 2026-10-30 | Release deployment | [R2026.NOV] [TIPS] Deployment of further scoped elements and release defects in UTEST |  |  | U
45 | 2026-11-04 | 2026-11-04 | Special testing |  |  | E |  |  | Billing period 19-31 October
45 | 2026-11-04 | 2026-11-04 | Special testing | BILL invoice for NCBs |  |  | U |  | Billing period 19-31 October
45 | 2026-11-06 | 2026-11-06 | Release deployment | [R2026.NOV] [TIPS] Deployment of further scoped elements and release defects in UTEST |  |  | U
47 | 2026-11-18 | 2026-11-18 | Special testing | BILL invoice for NCBs |  | E |  |  | Billing period 1-15 November
47 | 2026-11-18 | 2026-11-18 | Special testing | BILL invoice for NCBs |  |  | U |  | Billing period 1-15 November
49 | 2026-12-03 | 2026-12-03 | Special testing | BILL invoice for NCBs |  | E |  |  | Billing period 16-30 November
49 | 2026-12-03 | 2026-12-03 | Special testing | BILL invoice for NCBs |  |  | U |  | Billing period 16-30 November
51 | 2026-12-16 | 2026-12-16 | Special testing | BILL invoice for NCBs |  | E |  |  | Billing period 1-13 December
51 | 2026-12-16 | 2026-12-16 | Special testing | BILL invoice for NCBs |  |  | U |  | Billing period 1-13 December
2 | 2027-01-06 | 2027-01-06 | Special testing | BILL invoice for NCBs |  | E |  |  | Billing period 14-31 December
2 | 2027-01-06 | 2027-01-06 | Special testing | BILL invoice for NCBs |  |  | U |  | Billing period 14-31 December
4 | 2027-01-20 | 2027-01-20 | Special testing | [PLACEHOLDER] BILL invoice for NCBs |  |  | U |  | Billing period 01-17 January
6 | 2027-02-03 | 2027-02-03 | Special testing | [PLACEHOLDER] BILL invoice for NCBs |  |  | U |  | Billing period 17-31 January
10 | 2027-03-03 | 2027-03-03 | Special testing | [PLACEHOLDER] BILL invoice for NCBs |  |  | U |  | Billing period 01-28 February. Full month agreed through OMG WP.