## CBT-UT Calendar
Week number | Start Date | End Date | Activity type | Activity Name | Pending agreement | EAC | UTEST | PROD | Comments
47 | 2025-11-17 | 2025-11-30 | Schedule | TIPS EAC Billing Cycle 17/11 - 30/11 |  | E
49 | 2025-12-01 | 2025-12-14 | Schedule | TIPS EAC Billing Cycle 01/12 - 14/12 |  | E
49 | 2025-12-03 | 2025-12-03 | Special testing | BILL invoice for NCBs |  | E |  |  | Billing period 17-30 November
49 | 2025-12-03 | 2025-12-03 | Special testing | BILL invoice for NCBs |  |  | U |  | Billing period 01/11/-30/11/2025
51 | 2025-12-15 | 2025-12-31 | Schedule | TIPS EAC Billing Cycle 15/12 - 31/12 |  | E
51 | 2025-12-17 | 2025-12-17 | Special testing | BILL invoice for NCBs |  | E |  |  | Billing period 01-14 December
2 | 2026-01-06 | 2026-01-06 | Special testing | BILL invoice for NCBs |  | E |  |  | Billing period 15-31 December
2 | 2026-01-06 | 2026-01-06 | Special testing | BILL invoice for NCBs |  |  | U |  | Billing period 01/12/-31/12/2025
6 | 2026-02-04 | 2026-02-04 | Special testing | BILL invoice for NCBs |  | E |  |  | Billing period 01/01/2026-31/01/2026
6 | 2026-02-04 | 2026-02-04 | Special testing | BILL invoice for NCBs |  |  | U |  | Billing period 01/01/2026-31/01/2026
10 | 2026-03-04 | 2026-03-04 | Special testing | BILL invoice for NCBs |  | E |  |  | Billing period 01/02/-28/02/2026
10 | 2026-03-04 | 2026-03-04 | Special testing | BILL invoice for NCBs |  |  | U |  | Billing period 01/02/-28/02/2026
15 | 2026-04-07 | 2026-04-07 | Special testing | BILL invoice for NCBs |  | E |  |  | Billing period 01/03/-31/03/2026
15 | 2026-04-07 | 2026-04-07 | Special testing | BILL invoice for NCBs |  |  | U |  | Billing period 01/03/-31/03/2026
19 | 2026-05-06 | 2026-05-06 | Special testing | BILL invoice for NCBs |  | E |  |  | Billing period 01/04/-30/04/2026
19 | 2026-05-06 | 2026-05-06 | Special testing | BILL invoice for NCBs |  |  | U |  | Billing period 01/04/-30/04/2026
23 | 2026-06-03 | 2026-06-03 | Special testing | BILL invoice for NCBs |  | E |  |  | Billing period 01/05/-31/05/2026
23 | 2026-06-03 | 2026-06-03 | Special testing | BILL invoice for NCBs |  |  | U |  | Billing period 01/05/-31/05/2026
27 | 2026-07-03 | 2026-07-03 | Special testing | BILL invoice for NCBs |  | E |  |  | Billing period 01/06/-30/06/2026
27 | 2026-07-03 | 2026-07-03 | Special testing | BILL invoice for NCBs |  |  | U |  | Billing period 01/06/-30/06/2026
32 | 2026-08-05 | 2026-08-05 | Special testing | BILL invoice for NCBs |  | E |  |  | Billing period 01/07/-31/07/2026
32 | 2026-08-05 | 2026-08-05 | Special testing | BILL invoice for NCBs |  |  | U |  | Billing period 01/07/-31/07/2026
36 | 2026-09-03 | 2026-09-03 | Special testing | BILL invoice for NCBs |  | E |  |  | Billing period 01/08/-31/08/2026
36 | 2026-09-03 | 2026-09-03 | Special testing | BILL invoice for NCBs |  |  | U |  | Billing period 01/08/-31/08/2026
41 | 2026-10-05 | 2026-10-05 | Special testing | BILL invoice for NCBs |  | E |  |  | Billing period 01/09/-30/09/2026
41 | 2026-10-05 | 2026-10-05 | Special testing | BILL invoice for NCBs |  |  | U |  | Billing period 01/09/-30/09/2026
45 | 2026-11-04 | 2026-11-04 | Special testing | BILL invoice for NCBs |  | E |  |  | Billing period 01/10/-31/10/2026
45 | 2026-11-04 | 2026-11-04 | Special testing | BILL invoice for NCBs |  |  | U |  | Billing period 01/10/-31/10/2026
49 | 2026-12-03 | 2026-12-03 | Special testing | BILL invoice for NCBs |  | E |  |  | Billing period 01/11/-30/11/2026
49 | 2026-12-03 | 2026-12-03 | Special testing | BILL invoice for NCBs |  |  | U |  | Billing period 01/11/-30/11/2026
2 | 2027-01-06 | 2027-01-06 | Special testing | BILL invoice for NCBs |  | E |  |  | Billing period 01/12/-31/12/2026
2 | 2027-01-06 | 2027-01-06 | Special testing | BILL invoice for NCBs |  |  | U |  | Billing period 01/12/-31/12/2026