## CBT-UT Calendar
Week number | Start Date | End Date | Activity type | Activity Name | Pending agreement | EAC | UTEST | PROD | Comments
38 | 2026-09-16 | 2026-09-16 | Special testing | BILL invoice for NCBs |  | E |  |  | Billing period 1-13 September
38 | 2026-09-16 | 2026-09-16 | Special testing | BILL invoice for NCBs |  |  | U |  | Billing period 1-13 September
40 | 2026-09-28 | 2026-09-18 | Documentation | [R2026.NOV] [TIPS] Draft release note to UTEST |  |  | U
40 | 2026-10-01 | 2026-10-01 | Documentation | [R2026.NOV] [TIPS] Final release note to UTEST |  |  | U
41 | 2026-10-05 | 2026-10-05 | Special testing | BILL invoice for NCBs |  | E |  |  | Billing period 13-30 September
41 | 2026-10-05 | 2026-10-05 | Special testing | BILL invoice for NCBs |  |  | U |  | Billing period 13-30 September
41 | 2026-10-05 | 2026-10-08 | Release deployment | [R2026.NOV] [TIPS] Deployment of TIPS Release R2026.NOV to UTEST |  |  | U |  | The deployment for ISO related part will follow the same approach of R2026.JUN.
41 | 2026-10-08 | 2026-10-08 | Release deployment | [R2026.NOV] [TIPS] Deployment of CoCos to UTEST |  |  | U |  | Date in line with common deployment across all the TARGET Services
41 | 2026-10-09 | 2026-11-11 | Release testing | [R2026.NOV] [TIPS] User Testing in UTEST |  |  | U
42 | 2026-10-16 | 2026-10-16 | Release deployment | [R2026.NOV] [TIPS] Deployment of further scoped elements and release defects in UTEST |  |  | U
43 | 2026-10-21 | 2026-10-21 | Special testing | BILL invoice for NCBs |  | E |  |  | Billing period 1-18 October
43 | 2026-10-21 | 2026-10-21 | Special testing | BILL invoice for NCBs |  |  | U |  | Billing period 1-18 October
43 | 2026-10-23 | 2026-10-23 | Release deployment | [R2026.NOV] [TIPS] Deployment of further scoped elements and release defects in UTEST |  |  | U
44 | 2026-10-30 | 2026-10-30 | Release deployment | [R2026.NOV] [TIPS] Deployment of further scoped elements and release defects in UTEST |  |  | U
45 | 2026-11-04 | 2026-11-04 | Special testing | BILL invoice for NCBs |  | E |  |  | Billing period 19-31 October
45 | 2026-11-04 | 2026-11-04 | Special testing | BILL invoice for NCBs |  |  | U |  | Billing period 19-31 October
45 | 2026-11-06 | 2026-11-06 | Release deployment | [R2026.NOV] [TIPS] Deployment of further scoped elements and release defects in UTEST |  |  | U
47 | 2026-11-18 | 2026-11-18 | Special testing | BILL invoice for NCBs |  | E |  |  | Billing period 1-15 November
47 | 2026-11-18 | 2026-11-18 | Special testing | BILL invoice for NCBs |  |  | U |  | Billing period 1-15 November
47 | 2026-11-20 | 2026-11-20 | Release deployment | [R2026.NOV] [TIPS] Hotfix EAC for Postal Address Validation |  | E |  |  | [Unstructured address format for postal address: Update of TIPS validations to exclusively support strucutred and hybrid formats - Hotfix EAC deployment] 20/11/2026 As presented during the ad-hoc TIPS-WG ad-hoc meeting on 08/07/2026 - line added in this STP to provide claritiy to WG members
47 | 2026-11-20 | 2026-11-20 | Release deployment | [R2026.NOV] [TIPS] [Unstructured address format for postal address: Update of TIPS validations to exclusively support structured and hybrid formats - Hotfix UTEST deployment] |  |  | U |  | As presented during the ad-hoc TIPS-WG ad-hoc meeting on 08/07/2026
49 | 2026-12-03 | 2026-12-03 | Special testing | BILL invoice for NCBs |  | E |  |  | Billing period 16-30 November
49 | 2026-12-03 | 2026-12-03 | Special testing | BILL invoice for NCBs |  |  | U |  | Billing period 16-30 November
51 | 2026-12-16 | 2026-12-16 | Special testing | BILL invoice for NCBs |  | E |  |  | Billing period 1-13 December
51 | 2026-12-16 | 2026-12-16 | Special testing | BILL invoice for NCBs |  |  | U |  | Billing period 1-13 December
2 | 2027-01-06 | 2027-01-06 | Special testing | BILL invoice for NCBs |  | E |  |  | Billing period 14-31 December
2 | 2027-01-06 | 2027-01-06 | Special testing | BILL invoice for NCBs |  |  | U |  | Billing period 14-31 December