## CBT-UT Calendar
Week number | Start Date | End Date | Activity type | Activity Name | Pending agreement | EAC | UTEST | PROD | Comments
30 | 2026-07-22 | 2026-07-22 | Special testing | BILL invoice for NCBs |  | E |  |  | Billing period 1-19 July
30 | 2026-07-22 | 2026-07-22 | Special testing | BILL invoice for NCBs |  |  | U |  | Billing period 1-19 July
32 | 2026-08-04 | 2026-08-06 | Release deployment | [R2026.NOV] [TIPS] Deployment of TIPS Release R2026.NOV to EAC |  | E |  |  | Due to the dependency with the CoCo release and RTGS updates, the start of EAC deployment has been shifted from 27/7 to 4/8. SLA and BILL parts of CR-103 will be allocated within CoCo package 3 (i.e. delivey date in EAC = 03/09/2026). The deployment for ISO related part will follow the same approach of R2026.JUN.
32 | 2026-08-05 | 2026-08-05 | Special testing | BILL invoice for NCBs |  | E |  |  | Billing period 20-31 July
32 | 2026-08-05 | 2026-08-05 | Special testing | BILL invoice for NCBs |  |  | U |  | Billing period 20-31 July
32 | 2026-08-06 | 2026-08-06 | Release deployment | [R2026.NOV] TIPS Deployment of CoCos to EAC |  | E
32 | 2026-08-07 | 2026-09-11 | Release testing | [R2026.NOV] [TIPS] Eurosystem Acceptance Testing in EAC |  | E |  |  | On first day of rolling upgrade into EAC Due to dependencies with common components and message updates, the EAT phase start shall be postponed to 7/8. Testing for SLA and BILL parts of CR-103 can only start as of 03/09/2026.
33 | 2026-08-14 | 2026-08-14 | Release deployment | [R2026.NOV] [TIPS] Deployment of further scoped elements and release defects in EAC |  | E |  |  | Based on the need, the possible deployment of release defects or additional PBIs in the test environment would be scheduled on a Friday
34 | 2026-08-19 | 2026-08-19 | Special testing | BILL invoice for NCBs |  | E |  |  | Billing period 1-16 August
34 | 2026-08-19 | 2026-08-19 | Special testing | BILL invoice for NCBs |  |  | U |  | Billing period 1-16 August
34 | 2026-08-21 | 2026-08-21 | Release deployment | [R2026.NOV] [TIPS] Deployment of further scoped elements and release defects in EAC |  | E |  |  | Based on the need, the possible deployment of release defects or additional PBIs in the test environment would be scheduled on a Friday
35 | 2026-08-28 | 2026-08-28 | Release deployment | [R2026.NOV] [TIPS] Deployment of further scoped elements and release defects in EAC |  | E |  |  | Based on the need, the possible deployment of release defects or additional PBIs in the test environment would be scheduled on a Friday
36 | 2026-09-03 | 2026-09-03 | Special testing | BILL invoice for NCBs |  | E |  |  | Billing period 17-31 August
36 | 2026-09-03 | 2026-09-03 | Special testing | BILL invoice for NCBs |  |  | U |  | Billing period 17-31 August
36 | 2026-09-04 | 2026-09-04 | Release deployment | [R2026.NOV] [TIPS] Deployment of further scoped elements and release defects in EAC |  | E |  |  | Based on the need, the possible deployment of release defects or additional PBIs in the test environment would be scheduled on a Friday
37 | 2026-09-07 | 2026-09-11 | Special testing | [TIPS] 2026 E2E Volume Test - TIPS UTEST Environment TPS limit to be scaled up |  |  | U
38 | 2026-09-14 | 2026-09-14 | Documentation | [R2026.NOV] [TIPS] Draft release note to UTEST |  |  | U
38 | 2026-09-16 | 2026-09-16 | Special testing | BILL invoice for NCBs |  | E |  |  | Billing period 1-13 September
38 | 2026-09-16 | 2026-09-16 | Special testing | BILL invoice for NCBs |  |  | U |  | Billing period 1-13 September
38 | 2026-09-17 | 2026-09-17 | Documentation | [R2026.NOV] [TIPS] Final release note to UTEST |  |  | U
39 | 2026-09-21 | 2026-09-24 | Release deployment | [R2026.NOV] [TIPS] Deployment of TIPS Release R2026.NOV to UTEST |  |  | U |  | The deployment for ISO related part will follow the same approach of R2026.JUN.
39 | 2026-09-24 | 2026-09-24 | Release deployment | [R2026.NOV] [TIPS] Deployment of CoCos to UTEST |  |  | U |  | Date in line with common deployment across all the TARGET Services
39 | 2026-09-25 | 2026-10-28 | Release testing | [R2026.NOV] [TIPS] User Testing in UTEST |  |  | U
40 | 2026-10-02 | 2026-10-02 | Release deployment | [R2026.NOV] [TIPS] Deployment of further scoped elements and release defects in UTEST |  |  | U
41 | 2026-10-05 | 2026-10-05 | Special testing | BILL invoice for NCBs |  | E |  |  | Billing period 13-30 September
41 | 2026-10-05 | 2026-10-05 | Special testing | BILL invoice for NCBs |  |  | U |  | Billing period 13-30 September
41 | 2026-10-09 | 2026-10-09 | Release deployment | [R2026.NOV] [TIPS] Deployment of further scoped elements and release defects in UTEST |  |  | U
42 | 2026-10-16 | 2026-10-16 | Release deployment | [R2026.NOV] [TIPS] Deployment of further scoped elements and release defects in UTEST |  |  | U
43 | 2026-10-21 | 2026-10-21 | Special testing | BILL invoice for NCBs |  | E |  |  | Billing period 1-18 October
43 | 2026-10-21 | 2026-10-21 | Special testing | BILL invoice for NCBs |  |  | U |  | Billing period 1-18 October
45 | 2026-11-04 | 2026-11-04 | Special testing | BILL invoice for NCBs |  | E |  |  | Billing period 19-31 October
45 | 2026-11-04 | 2026-11-04 | Special testing | BILL invoice for NCBs |  |  | U |  | Billing period 19-31 October
47 | 2026-11-18 | 2026-11-18 | Special testing | BILL invoice for NCBs |  | E |  |  | Billing period 1-15 November
47 | 2026-11-18 | 2026-11-18 | Special testing | BILL invoice for NCBs |  |  | U |  | Billing period 1-15 November
47 | 2026-11-20 | 2026-11-20 | Release deployment | [R2026.NOV] [TIPS] Hotfix EAC for Postal Address Validation |  | E |  |  | [Unstructured address format for postal address: Update of TIPS validations to exclusively support strucutred and hybrid formats - Hotfix EAC deployment] 20/11/2026 As presented during the ad-hoc TIPS-WG ad-hoc meeting on 08/07/2026 - line added in this STP to provide claritiy to WG members
47 | 2026-11-20 | 2026-11-20 | Release deployment | [R2026.NOV] [TIPS] [Unstructured address format for postal address: Update of TIPS validations to exclusively support structured and hybrid formats - Hotfix UTEST deployment] |  |  | U |  | As presented during the ad-hoc TIPS-WG ad-hoc meeting on 08/07/2026
49 | 2026-12-03 | 2026-12-03 | Special testing | BILL invoice for NCBs |  | E |  |  | Billing period 16-30 November
49 | 2026-12-03 | 2026-12-03 | Special testing | BILL invoice for NCBs |  |  | U |  | Billing period 16-30 November
51 | 2026-12-16 | 2026-12-16 | Special testing | BILL invoice for NCBs |  | E |  |  | Billing period 1-13 December
51 | 2026-12-16 | 2026-12-16 | Special testing | BILL invoice for NCBs |  |  | U |  | Billing period 1-13 December
2 | 2027-01-06 | 2027-01-06 | Special testing | BILL invoice for NCBs |  | E |  |  | Billing period 14-31 December
2 | 2027-01-06 | 2027-01-06 | Special testing | BILL invoice for NCBs |  |  | U |  | Billing period 14-31 December