## CBT-UT Calendar
Week number | Start Date | End Date | Activity type | Activity Name | Pending agreement | EAC | UTEST | PROD | Comments
40 | 2025-10-01 | 2025-10-05 | Release deployment | Deployment of TIPS Release R2025.OCT to Production** |  |  |  | P | Rolling upgrade of TIPS PROD to R2025OCT. The deployment of TIPS Release R2025.OCT to the Production environment is scheduled to begin on Wednesday morning, 1 October 2025. However, to align with the European Payments Council (EPC) requirements for the October 2025 release, the deployment of the TIPS Message Routers -specifically for changes related to the SCT Inst 2025 Scheme Rulebook- will commence on Sunday, 5 October 2025, at 01:30 CEST. This rolling upgrade will be brief, with deployment expected to be fully completed by 03:30 CEST on the same morning. During the timeframe between 01:30 and 03:30 CEST on 5 October 2025, TIPS actors may encounter minor rejections related to the handling of the following elements on the TIPS users’ side: 1. Timestamp Handling 2. Missing Tags in camt.056 or pacs.004 messages
40 | 2025-10-05 | 2025-10-05 | Release deployment | End of deployment of TIPS Release R2025.OCT to Production |  |  |  | P | 4CB is assessing whether the deployment of the release can take place by means of a planned downtime, this will also depend on the analysis of the updated EPC SCT Inst scheme, which will be released in the second half of November. To be noted, VoP might still be done by mean of a rolling.
40 | 2025-10-05 | 2025-10-05 | Release deployment | TIPS Release R2025.OCT is live in Production |  |  |  | P
45 | 2025-11-05 | 2025-11-05 | Special testing | BILL invoice for NCBs |  | E |  |  | Billing period 01/10/-31/10/2025
45 | 2025-11-05 | 2025-11-05 | Special testing | BILL invoice for NCBs |  |  | U |  | Billing period 01/10/-31/10/2025
49 | 2025-12-03 | 2025-12-03 | Special testing | BILL invoice for NCBs |  | E |  |  | Billing period 01/11/-30/11/2025
49 | 2025-12-03 | 2025-12-03 | Special testing | BILL invoice for NCBs |  |  | U |  | Billing period 01/11/-30/11/2025
2 | 2026-01-06 | 2026-01-06 | Special testing | BILL invoice for NCBs |  | E |  |  | Billing period 01/12/-31/12/2025
2 | 2026-01-06 | 2026-01-06 | Special testing | BILL invoice for NCBs |  |  | U |  | Billing period 01/12/-31/12/2025